PUBLIC OUTREACH

Follow up Outreach to stakeholders as needed

Data Analysis/ Draft Strategies

[August 31, 2016]

Steering Committee Meeting #2

(May 4, 2016)

Public Hearing

[April 4 2017]

Steering Committee Meeting #3

[November 29, 2016]

Municipal Survey

[July 2016]

Stakeholder Input

* Key Farmers
* Agencies
* Consumers
* Educators

[On-going]

Public Meetings

[Fall 2016]

State of the Agricultural Economy

* Products
* Markets
* New Markets

[August 2016]

State of the County

Existing Conditions & Mapping

* Ag Districts
* Soils
* Protected Lands
* Farms
* Environmental Features, etc.

[August 2016]

Kick-Off Meeting

(10/15/15)

Steering Committee Meeting #4

[March 13, 2017]

FINAL PLAN

[April 30 2017]

DRAFT PLAN

[February 21, 2017]